## Summary
Westgate Entertainment District: power supply swaps
Window: May 1 to September 20, 2026. As of September 20, 2026.
Total power supplies swapped (counted)
Visits with a recorded count
Visits where supplies were replaced, count not recorded
Largest single visit
Still needed on site as of Sep 8 | 2
A visit with no count recorded is listed in the register and left out of the total.
Spare supply on site
Jun 5 | Last of the on-site supply used.
Jun 28 | 12 used in two days; another order requested.
Jul 6 | 20 more ordered.
Aug 18 | Shipment still in transit.
Aug 26 | Materials on site for the 17-unit visit.
Sep 8 | None left on site; 2 more needed.
Sep 10 | Replacement shipment due by end of day Sep 11.

## Visit Register
Date (2026) | On site | Case | Supplies swapped | What was done | Source
May 8 | Tim Harty (ANC) |  | not recorded | All outages fixed; every one was a failed power supply. Count not recorded. | Channel update, May 8
May 15 | Riley Chapman-Hart (ANC) |  | not recorded | Onsite for Screens 1, 2 and 6; power supplies changed on the other screens. Count not recorded. | Channel update, May 15
Jun 5 | Riley Chapman-Hart (ANC) |  | 2 | One on each board (Screens 2 and 3). Big blackouts fixed; one more supply short of 100%. | Channel update, Jun 5
Jun 24-25 | Riley Chapman-Hart (ANC) |  | 12 | 12 used across the two days (6 on day one), plus one faulty power cable swapped. | Riley's count to Nick, Jun 28
Jul 3 | Riley Chapman-Hart (ANC) |  | 3 | 3 used; 4 left on site afterwards. Screen 2 power run also repaired the same day. | Channel update, Jul 3
Aug 11 | Yesco |  | not recorded | Onsite at 6am with 3 new supplies available. Swap count not recorded. | Channel update, Aug 11
Aug 26 | Yesco | 00002222 | 17 | 17 power supplies, 3 modules and 2 power cables. 9 of 10 signs had outages; all fully illuminated on completion. | Case 00002222 / Yesco field report
Sep 3 | Yesco | 00002564 | 0 | Large outage was a failing data connector, not power; bypassed with new cable. Tech noted about 6 other power supply outages. | Case 00002564 tech notes
Sep 8 | Yesco | 00002565 | 7 | Board 6: 2, Board 7: 3, Board 8: 2. Two more needed with none left on site; 25+ modules flagged for RMA. | Case 00002565 Yesco notes
Total counted

## Part
Item | Value (manufacturer datasheet, V1.0)
Model | Rong Electric MDK300PC5
Output | +5.0 Vdc, 0-60 A, 300 W
Rated input | 100-240 Vac (range 90-264 Vac), 47-63 Hz
Efficiency | 90% or better at 220 Vac, full load
Power factor | 0.95 or better at full load
Cooling | Natural ventilation (self-cooled)
Protections | Input undervoltage, output current limiting, output short circuit